Publish Date

# CLASH MANAGEMENT

Company Name

8068-ORG-XX-XX-SP-X-5632

| Project Information |  |
| --- | --- |
| Lead Appointed Party Name | Lead Appointed Party Name |
| Company Name | Company Name |
| Company Address | Company Address |
| Originator Code | ORG |
| Client Name | Client Name |

| Project Details |  |
| --- | --- |
| Project Name | Project Name |
| Project Address | Project Address |
| Project Number | Project Number |
| Project Value | Project Value |
| Document Reference | 8068-ORG-XX-XX-SP-X-5632 |

| Document Status |  |
| --- | --- |
| Status | Status |
| Suitability | Suitability |
| Publish Date | Publish Date |

Document Issue

| Revision | Date | Author | Checked | Approved | Revision Comments |
| --- | --- | --- | --- | --- | --- |
| 01 | 12/05/2024 | J. Smith | M. Brown | T. Johnson | Initial draft completed. |

Document Location: C:\Users\Jarek Wityk\PDI Dropbox\Jarek Wityk\.PD\07_DigitalContent\0000_BIM Forms\8068-PDI-XX-XX-SP-X-5632_Clash Management.docx

Template Usage Instructions

Getting Started

Update Cover Logo: Right-click the large logo on the cover and select 'Change Picture' to replace it.

Second Page Logo: Similarly, right-click the logo on the second page and choose 'Change Picture' to update it.

Entering Data

Form Fields: The form fields are bordered in blue for easy identification. Start by entering data in the form fields on the second page; the Company Name and Client Name will propagate automatically across the document.

Document Issue Table: Update this table on the second page to reflect the current document issue details. (The Document Location will update automatically.)

Editing Document

Continued Data Entry: Proceed with entering data in the remaining form fields throughout the document.

Content Modification: Adjust the remaining content of the document as necessary.

Finalizing the Document

Updating References: Refresh the Table of Contents, table captions, figure captions, and Document Location by pressing CTRL+A then F9.

Clean-Up: Remove this instruction text box by deleting it.

THIS PAGE INTENTIONALLY LEFT BLANK.

TABLE OF CONTENTS

1. Introduction	5

2. Opening A Project	6

3. Setting Up 3D Views	8

4. Publishing A Model	11

5. ACC - Creating A Package	12

6. Creating A Clash	16

7. Solving A Clash	21

# Introduction

The following information shows a step-by-step process for the clash detection process used on sample project.

The clash detection process allows you to find asset between multiple models that are clashing.

Like a clash between a structural steel in the architectural model and containment in the electrical model:

On this project we clashed between 5 model

Electrical.

Mechanical.

Water Mist/Sprinkler.

Fire Alarm.

And Architectural.

We also had a security model but due to the security restrictions it was not part of the clash detection process. As it couldn’t be uploaded to the main Project Coordination view on the Autodesk construction cloud.

Throughout to the project we amassed over 1000 clashes between each model, by the end of the project all of the clashes will be rectified, and a clash free model can be handed over.

The following information is a step-by-step plan on how to open and solve a clash.

# Opening A Project

- Open the version of Revit you wish to use - Go to BIM 360/ACC

Go to Project files

Go to your project (ORG(Elec))

Open your Revit project.

Opening Worksets - Click OK

# Setting Up 3D Views

- Open your project, see step 1 for help.

Create A 3D View.

Go to View template.

Customize the Visibility Graphics to reflect the setting you wish.

The following screenshots show the setting we have set in the current model. Make sure you have all linked models turned off in the view, this is so you only publish the 3D model.

Name your 3D view

Go to the collaborate tab and select Publish Settings

Find the view you created and tick it.

As you can see above you can create multiple 3D view, when you add these to your publish settings you upload them all the BIM model. You can then add them to your project coordination view, and then clash detect within your own model.

# Publishing A Model

- Go to the collaborate tab

Go to manage cloud models

Go to the project you wish to publish

Publish The Model

# ACC - Creating A Package

Once the model has been prepared in Revit and published, the selected views will be available on ACC, ready to set up the clash detection.

Open web browser, navigate to your project in ACC, here the screenshot show ‘Docs’ panel, the landing page may be different.

Go to design collaboration.

Click the ellipsis to open the drop-down menu

Click the plus in the corner to begin creating a package.

Tick the box

Save

Click share

Add a short comment

The note should explain you have done since you last published the model and then press share. E.g.: Latest Updates

# Creating A Clash

- Open the Autodesk construction cloud

Go to model coordination

Go to views

Go to the coordination view that you have.

On the example the view is named project coordination

When you have opened the project coordination view. You will see a 3d model of the building you are working on.

When this model is open there will be 4 tabs in the right-hand corner. The third one down is called clashes and will allow you to create a clash

You can then select the primary model. The primary model for large-scale clash detection should be the main architectural model, as many of the assets in the model can’t be moved.

The clash with the drop-down bar will show a list of the other models that have been published and packaged in the Autodesk cloud. You then select the model you want to clash with. For example, Architectural (primary) and electrical (clash with). Or the architectural (primary), the electrical (clash with), and the mechanical (clash with).

The image below shows an example of the electrical model and all models clashing. In red are items that are clashing.

The next step is to click on the clash (in red) and click create an issue

When the clash is created, you can then type the issues.

Title: Who is a clash between. E.g. EL (for electrical), ME (for mechanical), and AR (for architecture). You then a small description E.g. Light clashing with railing.

Status: You can change the status between Open, In Review, Pending, and Closed. Open is what you use when you create an issue.

Type: Coordination.

Description: Is automatically entered when the clash is created.

Assigned to: Choose a designer from the company who is the cause of the clash.

Watchers: Whoever wishes to see when the issue is resolved.

Location: The Floor the clash is on.

Location details: Room number.

Due date: Unspecified.

Start date: Unspecified.

Root cause: This is either green (minor issue), amber (medium issue), and red (serious issue).

# Solving A Clash

- Open Autodesk construction cloud

Go to model coordination

Go to views

Go to the coordination view that you have. On the example the view is named project coordination

When you have opened the project coordination view. you will see a 3d model of the building you are working on.

The fourth one down is the issues tab

You can then filter and select what you want to appear

The only drop-down you select is status so that only the open issues appear. Also assigned, you select your name and/or people in your company to close all your issues.

When you find the clash, you are trying to solve, right-click on the clashing item and then click show properties

When have opened the show properties, can see the unique number that Revit applies to each asset. Copy this number

Go to the manage tab

Click on the select ID

Paste the code you got from show properties

They will highlight the asset in the Revit model. You move the asset to a new position to solve the clash. When the asset has been moved take a screenshot of the new position.

To see your changes on the Autodesk cloud you will publish the model and then create a package. Please see steps 4 and 5. When the model has been published and a package has been created. You can now go back to the issue or the issues that you changed in Revit and begin to complete the process of getting them closed

Then add the screenshot you took earlier and add the references, this proves that you moved it, in the Revit.

Also, add a short comment on what you have done